## Sheet1
Tasks | Duration (days) | Start Date | End Date | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07
Creat basic circuit for basic motor and servo control on the bike frame | 5 | 2017-10-16 | 2017-10-20
Basic responses to system perturbations, and PID tunning | 12 | 2017-10-23 | 2017-11-03
Bike upgrades; new flywheel design, installation of two flywheels, upgrade servos. | 5 | 2017-11-06 | 2017-11-10
Produce a stable balance in the frame, allowing for correction for external influences | 26 | 2017-11-06 | 2017-12-01
Holidays and exams | 40 | 2017-12-04 | 2018-01-12
Produced a controled lean and return to stable position | 19 | 2018-01-15 | 2018-02-02
Remove the bike system from the frame and install the wheels | 2 | 2018-02-05 | 2018-02-06
Produce the same stable balance, again allowing for corrections from external forces | 19 | 2018-02-05 | 2018-02-23
Produce a controlled lean with correction back to stable. | 19 | 2018-02-26 | 2018-03-16
Holidays | 28 | 2018-03-19 | 2018-04-15
Write Dissertation | 36 | 2018-04-02 | 2018-05-07